## Sheet
Task Name | Set Part | Parent Build | Start Date | End Date
design | Test Prop 1 | Horace's Home | 2016-12-05 | 2016-12-08
first build | Test Prop 1 | Horace's Home | 2016-12-19 | 2017-01-23
design | Test Prop 2 | Horace's Home | 2016-12-13 | 2016-12-16
first build | Test Prop 2 | Horace's Home | 2016-12-23 | 2017-01-23
design | Test Prop 2 | Horace's Home | 2017-01-09 | 2017-01-12
first build | Test Prop 3 | Horace's Home | 2017-01-23 | 2017-02-10
first build | Test Prop 4 |  | 2017-01-23 | 2017-02-07
first build | Test Prop 5 | Horace's Home | 2017-01-26 | 2017-02-08
duplicate build | Test Prop 1 | Horace's Home | 2017-03-20 | 2017-03-24
duplicate build | Test Prop 2 | Horace's Home 2 | 2017-03-20 | 2017-03-24